## Sample
Project Name | Rintis Payment Methode
Unit Part | WEB Product Development
PIC | Donny Maulana,S.Kom.,M.M.S.I
Total BreakDown | 34
Done | 100
On Going | 0
Meet Target | 82.3529
Delay | 17.6471
Total Days | 17.5
WorkLoad % | 47.1837
WorkLess % | 52.8163
Title | breakdown | Progress / breakdown % | Challenge | Hours | Start d/m/y H:I | Deadline | Exra time | Meet Target
Mocking UI Chekout | - UI/UX Topup Amount Logic | 100 |  | 4 | 2017-02-06 | 2017-02-07 |  | 1
| - UI/UX Package / Regristration Logic | 100 |  | 4 | 2017-02-06 | 2017-02-07 |  | 1
| - UI/UX VOD Rent | 100 |  | 8 | 2017-03-09 | 2017-03-10 |  | 1
| - Payment page ( part Indomaret ) | 100 |  | 8 | 2017-02-07 | 08/02/0201 | -3 day mid take leave ( 8, 9, 10 ) | 0 | 32 | 1
| - Payment page ( part Rintis ) | 100 |  | 8 | 2017-02-13 | 2017-02-14 |  | 1
| - Payment page ( part Doku ) | 100 |  | 8 | 2017-02-14 | 2017-02-15 |  | 1
| - Payment page ( part Bank Transfer ) | 100 |  | 4 | 2017-02-15 | 2017-02-15 |  | 1
| - Payment page ( part Creadit Card ) | 100 |  | 4 | 2017-02-15 | 2017-02-16 |  | 1
| - Succes Page doku | 100 |  | 4 | 2017-02-23 | 2017-02-24 | +16 mid late | 1
| - Invoice Indomaret | 100 |  | 4 | 2017-02-24 | 2017-02-24 |  | 1
| - Invoice Tranfer Bank | 100 |  | 4 | 2017-02-21 | 2017-02-21 |  | 1
| - Failed page no data transactin id | 100 |  | 4 | 2017-02-27 | 2017-02-27 |  | 1
| - Fail page Doku Response | 100 |  | 4 | 2017-02-24 | 2017-02-25 |  | 1
| - Email template payment | 100 |  | 4 | 2017-02-20 | 2017-02-20 |  | 1
Integrate UI with API | - Get API Checking Promo | 100 | Improvement | 4 | 2017-02-27 | 2017-02-28 |  | 1
| - implented UI to Api Promo | 100 |  | 4 | 2017-03-01 | 2017-03-01 |  | 1
| - Integrating API Push Checkout DOKU | 100 | SSL certificate cannot post url | 4 | 2017-02-28 | 2017-02-28 |  | 1
| - Validation Form post | 100 |  | 4 | 2017-03-01 | 2017-03-01 |  | 0
| - Get API Generate Rintis Code | 100 |  | 4 | 2017-03-06 | 2017-03-06 | delay 2 hari, test & debug | 0
| - Get Voucher logic & API | 100 |  | 4 | 2017-03-02 | 2017-03-02 |  | 1
| - Show Invoice code | 100 |  | 8 | 2017-03-03 | 2017-03-04 |  | 1
| - Parsing Doku request | 100 |  | 8 | 2017-02-22 | 2017-02-23 | delay 2 hari, test & debug | 0
| - Parsing Promo Doku Card Credit | 100 |  | 2 | 2017-03-06 | 2017-03-06 |  | 1
| - logic payment counting duration package | 100 |  | 2 | 2017-03-06 | 2017-03-06 |  | 1
| - logic promo event all transaction | 100 |  | 4 | 2017-03-06 | 2017-03-07 |  | 1
| - logic set cart payment | 100 |  | 4 | 2017-03-07 | 2017-03-07 |  | 1
| - logic for response after suces payment | 100 |  | 2 | 2017-03-07 | 2017-03-08 |  | 1
| - logic for all condition if failed transaction | 100 |  | 2 | 2017-02-17 | 2017-02-23 |  | 1 | 32
Testing and debug | - Test Topup with Rintis | 100 |  | 2 | 2017-03-20 | 2017-03-20 |  | 1
| - Test Pakage with Rintis | 100 |  | 2 | 2017-03-20 | 2017-03-20 |  | 1
| - Testing buying topup, package & topup doku | 100 |  | 2 | 2017-03-20 | 2017-03-20 |  | 1 | 32
| - Testing Payment include promo doku | 100 |  | 2 | 2017-03-20 | 2017-03-20 |  | 0
| - Revisi wording Before UAT | 100 |  | 2 |  |  |  | 0
| - Test Buy VOD with Rintis | 100 |  | 2 | 2017-03-21 | 2017-03-21 | extra finish 24 (include API Ready) | 1
100
8
| 2338800 | 2338800 | Total Est | 17.5 | days
116940
|  | Remider : | body email | sebelum taggal 21 |  |  | Calculate Date | 3.5
PerKatori mid time
2338800
49900
potongan promo | 116940
| 2271760 |  |  |  |  | Services |  | Help and Support |  | About Us | Payment Gateway
[6 empty] | 1 | Video On Demand | 1 | support@dens.tv | Features | 1
[6 empty] | 1 | TV Channel |  |  | Explore
[6 empty] | 1 | Social TV | 1 | Stay Social | FAQ
[6 empty] | 1 | Radio |  |  | Careers | Verified by
[6 empty] | 1 | Class Room |  |  |  | 1
Formulas:
Deadline = [Start d/m/y H:I]
Start d/m/y H:I = [Start d/m/y H:I, row above]
Start d/m/y H:I = [Deadline, row above]

## FIx
Project Name | PopcornTIme
Unit Part | Android Tv App Development
PIC | Muhammad eko aji saputro
Total BreakDown | =COUNT(J27:J42)
Done | =AVERAGE(D27:D42)
On Going | #VALUE!
Meet Target | 71.4286
Delay | 28.5714
Total Days | 6.125
WorkLoad % | =((C4/C9)/AVERAGE(F27:F42)*100)
WorkLess % | #VALUE!
Item | breakdown | Progress / breakdown % | Challenge | DAY | Start d/m/y H:I | Deadline | Exra time | Meet Target
Apps Build | Using Activities and Activity Life Cycles | 100 |  | 5 | 2023-04-03 | 2023-04-08 |  | 1
| Building Flexible Interfaces using Fragments | 100 |  | 3 | 2023-04-09 | 2023-04-12 |  | 1
| Debugging using Android Studio Debugger | 100 |  | 4 | 2023-04-13 | 2023-04-17 |  | 1
| Handling App Configurations | 100 | Improvement | 3 | 2023-04-18 | 2023-04-21 |  | 0
| Using Intents and Intent Filters | 50 |  | 3 | 2023-04-22 | 2023-04-25 | delay 2 hari, test & debug | 0
| Understand Context | 100 |  | 3 | 2023-04-26 | 2023-04-29 |  | 1
| Learn about Multithreading | 100 |  | 4 | 2023-04-09 | 2023-04-14 |  | 1
| Data Privacy | 50 | Improvement | 3 | 2023-04-10 | 2023-04-15 | delay 2 hari, test & debug | 0
| Securing Network Data | 100 |  | 2 | 2023-04-11 | 2023-04-16 |  | 1
| Dependency Injection | 0 |  | 2 | 2023-04-12 | 2023-04-17 |  | 1
| Content Providers | 0 |  | 4 | 2023-04-13 | 2023-04-18 |  | 0
| Glide, Retrofit, Crashlytics, GSON | 0 |  | 4 | 2023-04-14 | 2023-04-19 |  | 1
| Room, Navigation, Work Manager, LiveData, Data Binding | 0 |  | 2 | 2023-04-15 | 2023-04-20 |  | 1
| RxJava, RxKotlin | 0 |  | 2 | 2023-04-16 | 2023-04-21 |  | 1
| Memory Management Overview | 0 |  | 2 |  | 2023-04-22
| Diving deeper into context-oriented programming in Kotlin | 0 |  | 3 |  | 2023-04-23
37.5
8
|  |  | Total Est | 49 | days
0
[7 empty] | Calculate Date | 35
Note on C4: Microsoft Office User: aji Not Work with update data
Note on H33: Microsoft Office User: aji not update yet